## School development plan
Queen Mary Infant & Nursery School |  | Development plan 24-25 - priorities and milestones (see priority tabs for detailed actions) | [6 empty] | Notes: This document shows the 3-4 priorities for the current academic year. It is populated with some examples. The priorities are listed and then the intended outcomes (objectives) are set out - this is the ciritcal part of development planning. Be very clear what your outcome will be - be precise. After setting out your objectives for the END OF THE YEAR you can then work out the trajectory of how you will achieve that - this is shown through the milestones which will be achieved. These can then be BRAG rated to show governors how work is progressing. In this document add colours using the fill tool (Home tab) The detailed actions sit behind this summary plan and for each priority the actions will be listed on a new tab - see example on priority 1 tab and shorter example on priority 2 tab. Use the + button to add new tabs. | Evaluation code
Priorities |  | Objectives What will end points look like? | Milestones | [7 empty] | off track - unlikely to be completed
|  |  | Autumn 1 | Autumn 2 | Spring 1 | Spring 2 | Summer 1 | Summer 2 |  |  | in danger of going off track
1 | Continue to refine curriculum plans so that teachers know what pupils must learn. Add precision to support non-specialist teachers. | 1.1 100% Lessons all follow a clear sequence which builds on prior learning | Revise progression documents for DT and Computing. Share revised Art progression documents with teachers and begin to use. | Share revised progression documents with teachers and begin to use. Monitor and revise documents as required. Revise progression documents for PE and Music. | Share revised progression documents with teachers and begin to use. Monitor and revise documents as required. Identify key concepts in History | Share revised progression plans with teachers and begin to use. Monitor and revise documents as required. |  | Review RE curriculum plans in light of expected updates to Lincolnshire agreed syllabus |  |  | on track
|  | 1.2 Assessment shows that 70-80% children have met key objectives in foundation subjects. | Assessment shows that 70-80% children have met key objectives in History and Computing. | Assessment shows that 70-80% children have met key objectives in in DT and Music Revise assessment procedures for foundation subjetcs in EYFS | Assessment shows that 70-80% children have met key objectives in in Geography | Assessment shows that 70-80% children have met key objectives in Science | Assessment shows that 70-80% children have met key objectives in Art | Assessment shows that 70-80% children have met key objectives in PE. |  |  | complete
|  | 1.3 100% staff report improved subject knowledge for the units they teach in Music, DT, PE and Computing. Subject monitoring shows improved subject knowledge. |  | 100% staff report improved subject knowledge in DT and Computing |  | 100% staff report improved subject knowledge in Music and PE
|  | 1.4 Ensure curriculum is contextualised to meet the needs of our children. | CPD for curriculum lead | Staff to determine threads for curriculum plans linked to school context.
|  | 1.5 Assessment practices are consistent in 100% lessons |  | Curriculum lead introduces strategies for retrieval and assessment in Art. Develop strategies for DT, RE and Geography. | Develop retrieval strategies in Science, PE and Music |  |  | Monitoring shows that 100% staff use retrieval strategies introduced.
|  | 1.6 100% subject leaders analyse assessments to inform teaching and understand gaps in learning | Complete History and computing assessments. | History and computing lead to analyse assessment data. Complete DT and Music assessments | DT and Music lead to analyse assessment data. Complete Geography assessments | Geography lead to analyse assessment data. Complete Science assessments | Science lead to analyse assessment data. Complete Art assessments | Art lead to analyse assessment data. Complete PE assessments. PE lead to analyse data. |  | EXCEL TIPS If you want to start a new line in a cell use ALT and ENTER If text falls outside a cell use 'WRAP TEXT' to confine it Alter size of cell by dragging cell lines between numbers on the left hand side of the screen. To SAVE and circulate as a single document - PRINT to PDF To add a new line right click in the cell BELOW where you want the line and insert row. To rename a tab right click on it and select RENAME
2 | Further develop strategies to support pupils fluency in their reading | 2.1 Monitoring shows that 100% of staff are able to effectively model fluent reading with intonation. | Monitoring shows that 75% of teaching staff are able to effectively model fluent reading with intonation. | Monitoring shows that 75% of support staff are able to effectively model fluent reading with intonation. | Coaching/support is in place for staff in need of further support | Monitoring shows that 100% of staff are able to effectively model fluent reading with intonation. |  | Monitoring shows that 100% of staff are able to effectively model fluent reading with intonation.
|  | 2.2 For staff to consistently use strategies introduced by reader leader in RWI/reading lessons | 100% of KS1 teachers to trial use of echo reading. | Reading leader to deliver fluency training part 2 to teachers. Reading leader to develop fluency structure. | Reading leader to deliver fluency structure to teachers and TA's. | Reading leader to monitor the delivery of fluency and offer coaching and support. | Reading leader to gather feedback from staff on the structure of fluency. | Monitoring shows that 100% of staff are consistently and effectively delivery fluency. Reading leader to analyse data and measure impact.
|  | 2.3 Assessment processes meet the needs of our pupils and interventions are in place for children not on track in reading. | SLT to read Strong oundations in the first years of school. Implement RWI and reading fluency interventions for identified pupils. Analyse data to monitor progress | Teachers to read Stong foundations Trial use of York assessments to inform reading fluency interventions. RWI/fluency interventions in place Use info. from York assessments to inform fluency interventions. Make adaptations to end of term reading assessment procedures as needed. Analyse end of term data and monitor impact. |  | Make adaptations to end of term reading assessment procdesures as needed. Analyse end of term data. |  | Make adaptations to end of year reading assessment procdesures as needed. Analyse end of year data.
|  | 2.6 70-80% of pupils achieve age related expectations in reading (on track in RWI, Y1 phonics) | Baseline. 34% FS2 Autumn 1 57% Y1 72% Y2 phonics 53% Y2 Reading | 50-60% of pupils achieve age related expectations in reading (on track in RWI, Y1 phonics) |  | 60-70% of pupils achieve age related expectations in reading (on track in RWI, Y1 phonics) |  | 70-80% of pupils achieve age related expectations
3 | Continue to develop staff knowledge and understanding of SEND with a particular focus on - Intensive interaction - The Curiosity Programme and Attention Autism - Sensory provision - Smart targets | 3.1 100% of targets in PLPs are SMART, focus on area of need and have clear entry and exit points |  | Monitoring shows that targets in 80% of PLPs are SMART. SENDCo to support staff where needed. |  | Monitoring shows that targets in 90% of PLPs are SMART.SENDCo to support staff where needed. |  | Monitoring shows that targets in 100% of PLPs are SMART
|  | 3.3 100% of staff have improved understanding of - Intensive interaction - The Curiosity Programme and Attention Autism - Sensory provision - Smart targets | Intensive interaction CPD for all staff. Curiosity CPD and Making it Real Literacy CPD for BT. | Curiosity CPD for all staff. |  |  |  | Whole school BUSS training
|  | 3.3 100% of staff who deliver the following programmes are confident in doing so - Intensive Interaction - The Curiosity Programme and Attention Autism - Sensory interventions - BUSS Pilot | EYFS and Y1 teachers complete referals for Attention Autism | Begin to implement Intensive Interaction. CPD for Curiosity Programme (whole school) and Attention Autism (FS2) | Implement Attention Autism in FS2. CPD for Attention Autism (Nursery and Y1). | Introduction to BUSS CPD Monitor Intensive Interaction, Curiosity programme and Attention Autism. |  | BUSS Level 1 CPD x3 days. Monitor Intensive Interaction, Curiosity programme and Attention Autism.
|  | 3.4 100% of children with SEND achieve the best possible outcomes | SENDCo complete all Y2 special annual reviews | SEND progress reviews. Update PLPs Submit applications for EYIF | Analyse Autumn data Organise interventions Tas begin to use SEND overviews | SEND progress reviews Update PLPs Submit applications for EYIF | Analyse Spring data Organise interventions

## Priority 1
Objective | Action | Lead person | Start date | Finish date | Costs | RAG Rating | Monitoring | Status: Progress and/or Impact | Evaluator | Notes: Exemplar of the detailed/ operational actions to support a priority example taken from the previous tab (1.1) This was sorted by date after writing actions. Explore using the sort function to see how actions can be prioritised by date, person or RAG rating. EXCEL TIPS To extend box for RAG rating click on last colored cell, drag bottome left corner down the cells as far as is needed. To create a new page - copy layout onto a new tab. Then to add sort/ filter fuction highlight the column you wish to sort - Right click and choose sort or filter.
1.1 100% Lessons all follow a clear sequence which builds on prior learning
1.1 | Share revised Art progression plans with staff and begin to use. | AC | 2024-09-01 | 2024-09-01
1.1 | Revise progression plans for DT | AR | 2024-09-01 | 2024-10-01
1.1 | Share DT plans with staff and begin to use. | AR | 2024-10-01 | 2024-10-01 |  |  |  | Staff meeting led to improved teacher knowledge
1.1 | Review Autumn 1 History and Computing units with teachers | Teachers | 2024-11-01 | 2024-11-01 |  |  | BF SS
1.1. | Review DT plans after teaching as focus topic | Teachers | Dec 24/Jan 25 | Dec 24/Jan 25
1.1 | Revise progression plans for Computing | SS | 2024-09-01 | 2024-10-01
1.1 | Share Computing plans with staff and begin to use. | SS | 2024-11-01 | 2024-11-01
1.1. | Review Computing plans after teaching as focus topic | Teachers | Dec 24/Jan 25 | Dec 24/Jan 25
1.1 | Revise progression plans for PE | BT and AC | 2025-03-01 | 2025-04-01
1.1 | Share revised PE plans with staff and begin to use. | BT | 2025-05-01 | 2025-05-01
1.1 | Revise progression plans for Music | RM | 2025-03-01 | 2025-04-01 |  |  |  | Music plans need a wider review
1.1. | Share Music plans with staff and begin to use. | RM | 2025-05-01 | 2025-05-01 |  |  |  | To be shared after wider review
1.1. | Identify key concepts in History | BF | 2025-06-01 | 2025-06-01
1.1 | Share key concepts with staff | BF | 2025-07-01 | 2025-07-01
1.1. | Review RE curriculum plans in light of expected updates to Lincolnshire agreed syllabus | AC | 2025-05-01 | 2025-07-01
1.2 Assessment shows that 70-80% children have met key objectives in foundation subjects.
1.2 | Assessment shows that 70-80% children have met key ojectives in History. | BF | 2024-11-01 | 2024-11-01 |  |  |  | 70% plus for all objectives aside from 1 Y1 objective and 1 Y2 objective
1.2 | Assessment shows that 70-80% children have met key ojectives in Computing. | SS | 2024-11-01 | 2024-11-01
1.2 | DN and MC to revise assessment of foundation subjects in FS2 | MC DN | 2024-11-01 | 2024-12-01 |  |  |  | FS2 now using same system as KS1
1.2 | Assessment shows that 70-80% children have met key ojectives in DT | AR | 2025-01-01 | 2025-01-01 |  |  |  | N2 - 70%+ 3/6 objectives FS2 - 70%+ 5/5 taught objectives Y1 - 70%+ 3/6 objectives Y2- 70%+ 7/9 taught objectives
1.2 | Assessment shows that 70-80% children have met key ojectives in Music | RM | 2025-01-01 | 2025-01-01
1.2 | Assessment shows that 70-80% children have met key ojectives in Geography | SW | 2025-03-01 | 2025-03-01 |  |  |  | Y1 - 70% plus for 5/9 objectives Y2 - 70% plus1/9 objectives
1.2 | Assessment shows that 70-80% children have met key ojectives in Science | SS | 2025-05-01 | 2025-05-01
1.2 | Assessment shows that 70-80% children have met key ojectives in Art | AC | 2025-06-01 | 2025-06-01
1.2 | Assessment shows that 70-80% children have met key ojectives in PE | BT | 2025-09-01 | 2025-09-01
1.3 100% staff report improved subject knowledge for the units they teach in Music, DT, PE and Computing.
1.3 | Staff report improved subject knowledge for the units they teach in DT - questionnaire | Teachers | 2024-11-01 | 2024-11-01
1.3 | Staff report improved subject knowledge for the units they teach in Computing - questionnaire | Teachers | 2024-11-01 | 2024-11-01
1.3 | Staff report improved subject knowledge for the units they teach in Music - questionnaire | Teachers
1.3 | Staff report improved subject knowledge for the units they teach in PE - questionnaire | Teachers
1.4 Ensure curriculum is contextualised to meet the needs of our children.
1.4 | CPD for curriculum lead | AC | 2024-10-01 | 2024-12-01
1.4 | Staff to determine threads for curriculum plans linked to school context | Teachers | 2024-11-01 | 2024-12-01
1.5 Assessment practices are consistent in 100% lessons
1.5 | Curriculum lead introduces strategies for retrieval and assessment in Art. | AC | 2024-11-01 | 2024-11-01
1.5 | Develop retrieval and assessment strategies for DT. | AR | Sping 1 2025 | Sping 1 2025
1.5 | Develop retrieval and assessment strategies for Music | RM | Sping 1 2025 | Sping 1 2025
1.5 | Develop retrieval and assessment strategies for Geography. | SW | Sping 1 2025 | Sping 1 2025
1.5 | Develop retrieval strategies in Science | SS | Sping 1 2025 | Sping 1 2025
1.5 | Develop retrieval strategies in Art | JB | Sping 1 2025 | Sping 1 2025
1.5 | Develop retrieval strategies in PE | BT | Sping 1 2025 | Sping 1 2025
| Develop retrieval strategies in RE | AC | Sping 1 2025 | Sping 1 2025
1.6 100% subject leaders analyse assessments to inform teaching and understand gaps in learning
1.6 | Complete History and computing assessments. | Teachers | 2024-10-01 | 2024-10-01
1.6 | History lead to analyse assessment data. Address issues raised by assessments | BF | 2024-11-01 | 2024-11-01
1.6 | Computing lead to analyse assessment data. Address issues raised by assessments | SS | 2024-11-01 | 2024-11-01
1.6 | Complete DT and Music assessments. | Teachers | 2024-12-01 | 2024-12-01
1.6 | DT lead to analyse assessment data. Address issues raised by assessments | AR | 2025-01-01 | 2025-01-01
1.6 | Music lead to analyse assessment data. Address issues raised by assessments | RM | 2025-01-01 | 2025-01-01
1.6 | Complete Geography assessments. | Teachers | 2025-02-01 | 2025-02-01
1.6 | Geography lead to analyse assessment data. Address issues raised by assessments | SW | 2025-03-01 | 2025-03-01
1.6 | Complete Science assessments. | Teachers | 2025-04-01 | 2025-04-01
1.6 | Science lead to analyse assessment data. Address issues raised by assessments | SS | 2025-05-01 | 2025-05-01
1.6 | Complete Art assessments. | Teachers | 2025-05-01 | 2025-05-01
1.6 | Art lead to analyse assessment data. Address issues raised by assessments | AC | 2025-06-01 | 2025-06-01
1.6 | Complete PE assessments. | Teachers | 2025-07-01 | 2025-07-01
1.6 | PE lead to analyse assessment data. Address issues raised by assessments | BT | 2025-09-01 | 2025-09-01

## Priority 2
Objective | Action | Lead person | Start date | Finish date | Costs | Monitoring | RAG Rating | Status: Progress and/or Impact | Evaluator
2.1 Monitoring shows that 100% of staff are able to effectively model fluent reading with intonation.
2.1 | RWI Training Day - July - focusing on reading section of lesson | ST | 2024-07-22 | 2024-07-22 | 0 | ST
2.1 | Monitor staff modelling of fluency | ST | 2024-09-23 | 2024-10-18 | 0 | ST
2.1 | Coaching/support for identfied staff | ST | Jan/Feb 2025 | Jan/Feb 2025 | 0 | ST
2.1 | Further monitoring | ST | Mar/Apr | Mar/Apr | 0 | ST
2.2 For staff to consistently use strategies introduced by reader leader in RWI/reading lessons
2.2 | Fluency training day one - Literacy hub | ST EJ | 2024-09-19 | 2020-09-29 | 0
2.2 | Discuss with SLT | ST | 2024-09-24 | 2024-09-24 | 0 | NA
2.2 | Staff meeting intro - teachers | ST | 2024-10-10 | 2024-10-10 | 0 | NA
2.2 | KS1 teachers to trial use of echo reading | KS1 teachers | 2024-10-01 | 2024-12-01 | 0
2.2 | Fluency training day two - Literacy hub | ST EJ | 2024-11-04 | 2024-11-04 | 0 | NA
2.2 | Relook/speak with Kally about how fluency taught in RWI (RWI dev day) | ST DN | 2024-11-01 | 2024-11-01 | 1500
2.2 | Staff meeting - session two | ST | 2024-12-12 | 2024-12-12 | 0
2.2 | TA meeting | ST | 2025-01-01 | 2025-01-01 | 0
2.2 | Revise the texts used on the reading spine and update as required | ST AT DN | 2025-01-01 | 2025-02-01 | 0
2.2 | Develop fluency structure | ST EJ | 2024-12-01 | 2024-12-01 | 0
2.2 | Fluency language | ST
2.2 | Share fluency structure with all staff - monitor delivery and offer coaching/support | ST | 2025-01-01 | 2025-02-01 | 0
2.2 | Reading leader to gather feedback from staff on the structure of fluency. | ST | 2025-02-01 | 2025-02-01 | 0
2.2 | Monitoring of fluency delivery. | ST | 2025-03-01 | 2025-04-01
2.2 | Reading leader to analyse data and measure impact. | ST | Termly |  |  |  |  | Autumn data shows good impact
2.3 Assessment processes meet the needs of our pupils and interventions are in place for children not on track in reading.
2.3 | Half-termly RWI assessments | ST MC DN | Half-termly |  | 0
2.3 | Implement RWI and reading fluency interventions for identified pupils. | ST MC DN | Half-termly |  | 0
2.3 | Analyse progress of children with interventions | ST MC | 2024-10-01 | 2024-10-01 | 0 |  |  | Progress Y1 - 65% inc EHCP 77% ex EHCP Y2 - 66% inc EHCP 69% exc EHCP Y2 Fluency - 86%
2.3 | SLT to read Strong foundations in the first years of school. | SLT | 2024-11-01 | 2024-11-01 | 0
2.3 | Introduce York Assessment for fluency/comp | ST EJ | 2025-01-01 | 2025-01-01 |  |  |  | Introduced for selected children as needed
2.3 | Make adaptations to end of term reading assessment procedures as needed. | ST MC
2.3 | Analyse end of term data. | ST MC | 2024-12-01 | 2025-01-01 | 0 |  |  | See below
2.3 | Phonic Screening | KS1 teachers | Feb-25 |  | 0 |  |  | Baseline Y1 39% Feb Y2 72% June 78% Feb
2.3 | Analyse progress of children with interventions | ST MC | 2025-02-01 | 2025-02-01 | 0 |  |  | Progress FS2 - 53% Y1 - 71% inc EHCP 79% ex EHCP Y2 - 72% inc EHCP 73% exc EHCP Y2 Fluency - 95%
2.4 70-80% of pupils achieve age related expectations in reading (on track in RWI, Y1 phonics)
2.4 | Baseline reading data | MC | Sep-24 |  | 0 | ST |  | 34% FS2 Autumn 1 57% Y1 53% Y2 Reading
2.4 | Making it Real CPD - early language development | BT | 2024-09-18 | 2024-09-25 | Cover | NA
2.4 | Making it Real team to engage with parents at Nursery stay and play | BT | 2024-10-08 | 2024-10-11 | 0
2.4 | Reading for pleasure CPD | ST | 2024-10-09 | 2024-10-09 | 0
2.4 | Reconsider RWI and KS1 timetable | SLT | 2024-09-25 | 2024-09-26 | 0 | ST |  | RWI now 50 mins allowing more time for reading
2.4 | Reading in the curriculum course - Literacy Hub | AC | 2024-11-21 | 2024-11-21 | 0 | NA
2.4 | Promote Rainbow Reading challenge - newlsetters, social media, open afternoons | Teachers | 2024-09-01 | 2025-07-01 | 0 |  |  | How many on challenge
2.4 | Monitor reading data | MC | 2024-10-01 | 2024-10-01 | 0 | ST |  | 34% FS2 Autumn 1 55% Y1 53% Y2
2.4 | Monitor reading data | MC | 2024-12-01 | 2024-12-01 | 0 | ST |  | 49% FS2 55% Y1 49% Y2
2.4 | Monitor reading data | MC | 2025-02-01 | 2025-02-01 | 0 | ST |  | 48% FS2 (3 children left) 55% Y1 53% Y2

## Priority 3
Objective | Action | Lead person | Start date | Finish date | Costs | Monitoring | RAG Rating | Status: Progress and/or Impact | Evaluator
3.1 100% of targets in PLPs are SMART, focus on area of need and have clear entry and exit points
3.1 | Monitoring shows that targets in 80% of PLPs are SMART. SENDCo to support staff where needed. | ES | 2024-10-01 |  | 0 |  |  | 90% of targets in PLPs are SMART.
3.1 | Monitoring shows that targets in 80% of PLPs are SMART. SENDCo to support staff where needed. | ES | 2025-03-01
3.2 100% of staff have improved understanding of Intensive interaction, The Curiosity Programme, Attention Autism, Sensory provision. Staff deliver programmes with confidence
3.2 | Intensive interaction CPD with Paul Cook | MC | 2024-09-26 | 2024-09-26 | 100
3.2 | BT attend Curiosity CPD | BT | 2024-09-10 | 2024-09-10 | 0
3.2 | Disseminate Curiosity CPD | BT | 2024-12-05 | 2024-12-05 | 0
3.2 | Complete Attention Autism referals | ES/MC | 2024-10-01 | 2024-11-01 | 0
3.2 | EYFS team to model Attention Autism in FS2 | MC | 2024-11-01 | 2024-11-01 | 0
3,2 | FS2 staff to model Attention Autism to N and Y1 staff | LC | 2024-11-01 | 2024-11-01 | 0
3.2 | Begin to implement Attention Autism in N-Y1 | TA | Spring 25 | Spring 25 | 0
3.3 100% of children with SEND achieve the best possible outcomes
3.3 | SENDCo complete all Y2 special annual reviews | ES | 2024-09-01 | 2024-10-01 | 0 | NA
3.3 | EYIF applications | ES BT | 2024-10-01 | 2024-10-01
3.3 | SEND Learning walk | ES
3.3 | Analye RWI data and review interventions | MC ST
3.3 | EYIF applications | ES BT | 2025-03-01 | 2025-03-01