## School development plan
Queen Mary Infant & Nursery School |  | Development plan 24-25 - priorities and milestones (see priority tabs for detailed actions) | [6 empty] | Notes: This document shows the 3-4 priorities for the current academic year. It is populated with some examples. The priorities are listed and then the intended outcomes (objectives) are set out - this is the ciritcal part of development planning. Be very clear what your outcome will be - be precise. After setting out your objectives for the END OF THE YEAR you can then work out the trajectory of how you will achieve that - this is shown through the milestones which will be achieved. These can then be BRAG rated to show governors how work is progressing. In this document add colours using the fill tool (Home tab) The detailed actions sit behind this summary plan and for each priority the actions will be listed on a new tab - see example on priority 1 tab and shorter example on priority 2 tab. Use the + button to add new tabs. | Evaluation code
Priorities |  | Objectives What will end points look like? | Milestones | [7 empty] | off track - unlikely to be completed
|  |  | Autumn 1 | Autumn 2 | Spring 1 | Spring 2 | Summer 1 | Summer 2 |  |  | in danger of going off track
1 | Continue to refine curriculum plans so that teachers know what pupils must learn. Add precision to support non-specialist teachers. | 1.1 100% Lessons all follow a clear sequence which builds on prior learning | Revise progression documents for DT and Computing. Share revised Art progression documents with teachers and begin to use. | Share revised progression documents with teachers and begin to use. Monitor and revise documents as required. Revise progression documents for PE and Music. | Share revised progression documents with teachers and begin to use. Monitor and revise documents as required. Identify key concepts in History |  |  | Review RE curriculum plans in light of expected updates to Lincolnshire agreed syllabus. Share key concepts for History |  |  | on track
|  | 1.2 Assessment shows that 70-80% children have met key objectives in foundation subjects. | Assessment shows that 70-80% children have met key objectives in History and Computing. | Assessment shows that 70-80% children have met key objectives in in DT and Music Revise assessment procedures for foundation subjetcs in EYFS | Assessment shows that 70-80% children have met key objectives in in Geography | Assessment shows that 70-80% children have met key objectives in Science | Assessment shows that 70-80% children have met key objectives in Art | Assessment shows that 70-80% children have met key objectives in PE. |  |  | complete
|  | 1.3 Assessment practices are consistent in 100% lessons |  | Curriculum lead introduces strategies for retrieval and assessment in Art. Develop strategies for DT, RE and Geography. | Develop retrieval strategies in Science, PE and Music |  |  | Monitoring shows that 100% staff use retrieval strategies introduced.
|  | 1.4 100% subject leaders analyse assessments to inform teaching and understand gaps in learning | Complete History and computing assessments. | History and computing lead to analyse assessment data. Complete DT and Music assessments | DT and Music lead to analyse assessment data. Complete Geography assessments | Geography lead to analyse assessment data. Complete Science assessments | Science lead to analyse assessment data. Complete Art assessments | Art lead to analyse assessment data. Complete PE assessments. PE lead to analyse data. |  | EXCEL TIPS If you want to start a new line in a cell use ALT and ENTER If text falls outside a cell use 'WRAP TEXT' to confine it Alter size of cell by dragging cell lines between numbers on the left hand side of the screen. To SAVE and circulate as a single document - PRINT to PDF To add a new line right click in the cell BELOW where you want the line and insert row. To rename a tab right click on it and select RENAME
2 | Further develop strategies to support pupils fluency in their reading | 2.1 Monitoring shows that 100% of staff are able to effectively model fluent reading with intonation. | Monitoring shows that 75% of teaching staff are able to effectively model fluent reading with intonation. | Monitoring shows that 75% of support staff are able to effectively model fluent reading with intonation. | Coaching/support is in place for staff in need of further support | Monitoring shows that 100% of staff are able to effectively model fluent reading with intonation. |  | Monitoring shows that 100% of staff are able to effectively model fluent reading with intonation.
|  | 2.2 For staff to consistently use strategies introduced by reader leader in RWI/reading lessons | 100% of KS1 teachers to trial use of echo reading. | Reading leader to deliver fluency training part 2 to teachers. Reading leader to develop fluency structure. | Reading leader to deliver fluency structure to teachers and TA's. | Reading leader to monitor the delivery of fluency and offer coaching and support. | Reading leader to gather feedback from staff on the structure of fluency. | Monitoring shows that 100% of staff are consistently and effectively delivering fluency. Around 80% of staff delivering confidently in July monitoring. Reading leader to analyse data and measure impact.
|  | 2.3 Assessment processes meet the needs of our pupils and interventions are in place for children not on track in reading. | SLT to read Strong Foundations in the first years of school. Implement RWI and reading fluency interventions for identified pupils. Analyse data to monitor progress | Teachers to read Stong foundations Trial use of York assessments to inform reading fluency interventions. RWI/fluency interventions in place Use info. from York assessments to inform fluency interventions. Make adaptations to end of term reading assessment procedures as needed. Analyse end of term data and monitor impact. |  | Make adaptations to end of term reading assessment procdesures as needed. Analyse end of term data. |  | Make adaptations to end of year reading assessment procdesures as needed. Analyse end of year data.
|  | 2.6 70-80% of pupils achieve age related expectations in reading (on track in RWI, Y1 phonics) | Baseline. 38% FS2 61% Y1 phonics 72% Y2 phonics 50% Y2 Reading | Target - 50-60% of pupils achieve age related expectations in reading (on track in RWI, Y1 phonics) Autumn 2 34% FS2 Autumn 1 57% Y1 72% Y2 phonics 48% Y2 Reading |  | Target 60-70% of pupils achieve age related expectations in reading (on track in RWI, Y1 phonics) Spring 2 46% FS2 62% Y1 76% Y2 phonics 53% Y2 Reading |  | Target 70-80% of pupils achieve age related expectations Summer 2 60% FS2 67% non EHCP 54% Y1 60% non EHCP 69% Y1 phonics 62% Y2 Reading 66% non EHCP 84% Y2 phonics
3 | Continue to develop staff knowledge and understanding of SEND with a particular focus on - Intensive interaction - The Curiosity Programme and Attention Autism - Sensory provision - Smart targets | 3.1 100% of targets in PLPs are SMART, focus on area of need and have clear entry and exit points |  | Monitoring shows that targets in 80% of PLPs are SMART. SENDCo to support staff where needed. |  | Monitoring shows that targets in 90% of PLPs are SMART. SENDCo to support staff where needed. |  | Monitoring shows that targets in 100% of PLPs are SMART. SENDCo to support staff where needed.
|  | 3.3 100% of staff have improved understanding of - Intensive interaction - The Curiosity Programme and Attention Autism - Sensory provision - Smart targets | Intensive interaction CPD for all staff. Curiosity CPD and Making it Real Literacy CPD for BT. | Curiosity CPD for all staff. | Attention Autism CPD for relevant staff | Model Attention Autism for relevant staff | Further modelling of Attention Autism for relevant staff as needed
|  | 3.3 100% of staff who deliver the following programmes are confident in doing so - Intensive Interaction - The Curiosity Programme and Attention Autism - Sensory interventions - BUSS Pilot | EYFS and Y1 teachers complete referals for Attention Autism | Begin to implement Intensive Interaction. CPD for Curiosity Programme (whole school) and Attention Autism (FS2) | Implement Attention Autism in FS2. CPD for Attention Autism (Nursery and Y1). | Introduction to BUSS CPD Monitor Intensive Interaction, Curiosity programme and Attention Autism. | Identify pupils for Autumn 2025 Leaplets group (BUSS) | Engage with parents of identifed BUSS children and cooomuncate details of Leaplets sessions for Autumn 2025
|  | 3.4 100% of children with SEND achieve the best possible outcomes | SENDCo complete all Y2 special annual reviews | SEND progress reviews. Update PLPs Submit applications for EYIF | Analyse Autumn data Organise interventions Tas begin to use SEND overviews | SEND progress reviews Update PLPs Submit applications for EYIF Analyse progress against PLP targets | Analyse Spring data Organise interventions | SEND progress reviews Update PLPs Analyse progress against PLP targets

## Priority 1
Objective | Action | Lead person | Start date | Finish date | Costs | RAG Rating | Monitoring | Status: Progress and/or Impact | Evaluator | Notes: Exemplar of the detailed/ operational actions to support a priority example taken from the previous tab (1.1) This was sorted by date after writing actions. Explore using the sort function to see how actions can be prioritised by date, person or RAG rating. EXCEL TIPS To extend box for RAG rating click on last colored cell, drag bottome left corner down the cells as far as is needed. To create a new page - copy layout onto a new tab. Then to add sort/ filter fuction highlight the column you wish to sort - Right click and choose sort or filter.
1.1 100% Lessons all follow a clear sequence which builds on prior learning
1.1 | Share revised Art progression plans with staff and begin to use. | AC | 2024-09-01 | 2024-09-01 | 0 |  | AC |  | Governors
1.1 | Revise progression plans for DT | AR | 2024-09-01 | 2024-10-01 | HLTA cover £205 per day |  | AR |  | Governors
1.1 | Share DT plans with staff and begin to use. | AR | 2024-10-01 | 2024-10-01 | 0 |  | AR | Staff meeting led to improved teacher knowledge | Governors
1.1 | Review Autumn 1 History and Computing units with teachers | Teachers | 2024-11-01 | 2024-11-01 | 0 |  | BF SS |  | Governors
1.1. | Review DT plans after teaching as focus topic | Teachers | Dec 24/Jan 25 | Dec 24/Jan 25 | HLTA cover £205 per day |  | AR | Review complete. Soe issues identifed with DT plans during Summer SIP visit. To be addressed Autumn 25 | Governors
1.1 | Revise progression plans for Computing | SS | 2024-09-01 | 2024-10-01 | HLTA cover £205 per day |  | SS | Review complete. See updated progression documents | Governors
1.1 | Share Computing plans with staff and begin to use. | SS | 2024-11-01 | 2024-11-01 | 0 |  | SS | Review complete. See updated Long Term Plan. Update July 2025 - staff are finding it tricky to fit in all aspects of planned lessons. To review further with SIP in Autumn 2025 | Governors
1.1 | Revise progression plans for PE | BT and AC | 2025-03-01 | 2025-04-01 | HLTA cover £205 per day |  | AC BT | The PE Long Term Plan and progression document has been updated. Further updates are needed 2025-26 to identify specific PE lessons to be taught in each year group to ensure coverage and progression. | Governors
1.1 | Revise progression plans for Music | RM | 2025-03-01 | 2025-04-01 | HLTA cover £205 per day |  | RS | Music plans need a wider review. Music lead met Zoe H with from music hub. Visited Littleoates 16/7 to see Sparkyards Music Scheme Sparkyards Programme purchased ready for use in Autumn 2025. CPD delivered July 2025. | Governors
1.1. | Share Music plans with staff and begin to use. | RM | 2025-05-01 | 2025-05-01 | 0 |  | RS | To be shared after wider review | Governors
1.1. | Identify key concepts in History | BF | 2025-06-01 | 2025-06-01 | 0 |  |  |  | Governors
1.1 | Share key concepts with staff | BF | 2025-07-01 | 2025-07-01 | 0 |  |  |  | Governors
1.1. | Review RE curriculum plans in light of expected updates to Lincolnshire agreed syllabus | AC | 2025-05-01 | 2025-07-01 | LDBE RE Curriculum £145 |  |  | CPD Wednesday 9th July. To start using new plans September 2025 | Governors
Governors
1.2 Assessment shows that 70-80% children have met key objectives in foundation subjects.
1.2 | Assessment shows that 70-80% children have met key ojectives in History. | BF | 2024-11-01 | 2024-11-01 | Insight £1250 |  | MC | FS2 - 70%+ 2/5 taught objectives Y1 - 70%+ 9/9 taught objectives Y2 - 70%+ 9/9 taught objectives | Governors
1.2 | Assessment shows that 70-80% children have met key ojectives in Computing. | SS | 2024-11-01 | 2024-11-01 | Insight £1250 |  | MC | Y1 - 70%+ 5/5 taught objectives Y2 - 70%+ 3/3 taught objectives | Governors
1.2 | DN and MC to revise assessment of foundation subjects in FS2 | MC DN | 2024-11-01 | 2024-12-01 | Insight £1250 |  | MC | FS2 now using same system as KS1 | Governors
1.2 | Assessment shows that 70-80% children have met key ojectives in DT | AR | 2025-01-01 | 2025-01-01 | Insight £1250 |  | MC | FS2 - 70%+ 5/5 taught objectives Y1 - 70%+ 8/12 taught objectives Y2- 70%+ 7/9 taught objectives | Governors
1.2 | Assessment shows that 70-80% children have met key ojectives in Music | RM | 2025-01-01 | 2025-01-01 | Insight £1250 |  | MC | FS2 - 70% plus for 7/8 objectives Y1 - 70% plus for 4/5 taught objectives Y2 - 70% plus 3/3 taught objectives | Governors
1.2 | Assessment shows that 70-80% children have met key ojectives in Geography | SW | 2025-03-01 | 2025-03-01 | Insight £1250 |  | MC | FS2 - 70%+ for 4/5 taught objects (67% for remaining objective) Y1 - 70% plus for 9/12 taught objectives Y2 - 70% plus 5/8 taught objectives (other objectives 60%+) | Governors
1.2 | Assessment shows that 70-80% children have met key ojectives in Science | SS | 2025-05-01 | 2025-05-01 | Insight £1250 |  | MC | FS2 - 70%+ for 8/8 taught objects (67% for remaining objective) Y1 - 70% plus for 9/12 taught objectives Y2 - 70% plus 6/9 taught objectives | Governors
1.2 | Assessment shows that 70-80% children have met key ojectives in Art | AC | 2025-06-01 | 2025-06-01 | Insight £1250 |  | MC | FS2 - 70%+ for 11/14 taught objects Y1 - 70% plus for 6/7 taught objectives Y2 - 70% plus for all taught objectives | Governors
1.2 | Assessment shows that 70-80% children have met key ojectives in PE | BT | 2025-09-01 | 2025-09-01 | Insight £1250 |  | MC |  | Governors
1.3 Assessment practices are consistent in 100% lessons
1.3 | Curriculum lead introduces strategies for retrieval and assessment in Art. | AC | 2024-11-01 | 2024-11-01 | HLTA cover £102 |  | AC | Recent learning walk - all staff using retrieval as part of practice. Pitch was appropriate and delivery was good. Variety of actvites seen and vocab was recapped and taught well. Next steps - to ensure appropriate pace for retrieval section of lesson. | Governors
1.3 | Develop retrieval and assessment strategies for DT. | AR | Spring 1 2025 | Spring 1 2025 | HLTA cover £102 |  | AC
1.3 | Develop retrieval and assessment strategies for Music | RM | Spring 1 2025 | Spring 1 2025 | HLTA cover £102 |  | AC
1.3 | Develop retrieval and assessment strategies for Geography. | SW | Spring 1 2025 | Spring 1 2025 | HLTA cover £102 |  | AC
1.3 | Develop retrieval and assessment strategies for PSHE | DN | Spring 1 2025 | Spring 1 2025 | HLTA cover £102 |  | AC
1.3 | Develop retrieval and assessment strategies for Computing. | SS | Spring 1 2025 | Spring 1 2025 | HLTA cover £102 |  | AC
1.3 | Develop retrieval strategies in Art | JB | Spring 1 2025 | Spring 1 2025 | HLTA cover £102 |  | AC
1.3 | Develop retrieval strategies in Science | SS | Spring 2 2025 | Spring 2 2025 | HLTA cover £102 |  | AC
1.3 | Develop retrieval strategies in PE | BT | Summer 1 2025 | Summer 1 2025 | HLTA cover £102 |  | AC
1.3 | Develop retrieval strategies in RE | AC | Summer 2 2025 | Summer 2 2025 | HLTA cover £102 |  | AC
[8 empty] | D | Governors
1.4 100% subject leaders analyse assessments to inform teaching and understand gaps in learning
1.4 | History lead to analyse assessment data. Address issues raised by assessments | BF | 2024-11-01 | 2024-11-01 | HLTA cover £102 |  | AC MC | See subject leader data summary sheet for details of strengths/areas for development. | Governors
1.4 | DT lead to analyse assessment data. Address issues raised by assessments | AR | 2025-01-01 | 2025-01-01 | HLTA cover £102 |  | AC MC |  | Governors
1.4 | Music lead to analyse assessment data. Address issues raised by assessments | RM | 2025-01-01 | 2025-01-01 | HLTA cover £102 |  | AC MC |  | Governors
1.4 | Geography lead to analyse assessment data. Address issues raised by assessments | SW | 2025-03-01 | 2025-03-01 | HLTA cover £102 |  | AC MC |  | Governors
1.4 | Computing lead to analyse assessment data. Address issues raised by assessments | Teachers | 2025-04-01 | 2025-04-01 | HLTA cover £102 |  | AC MC |  | Governors
1.4 | Music lead to analyse assessment data. Address issues raised by assessments | Teachers | 2025-05-01 | 2025-05-01 | HLTA cover £102 |  | AC MC |  | Governors
1.4 | Science lead to analyse assessment data. Address issues raised by assessments | SS | 2025-05-01 | 2025-05-01 | HLTA cover £102 |  | AC MC |  | Governors
1.4 | Art lead to analyse assessment data. Address issues raised by assessments | JB | 2025-06-01 | 2025-06-01 | HLTA cover £102 |  | AC MC |  | Governors
1.4 | PE lead to analyse assessment data. Address issues raised by assessments | BT | 2025-09-01 | 2025-09-01 | HLTA cover £102 |  | AC MC |  | Governors

## Priority 2
Objective | Action | Lead person | Start date | Finish date | Costs | Monitoring | RAG Rating | Status: Progress and/or Impact | Evaluator
2.1 Monitoring shows that 100% of staff are able to effectively model fluent reading with intonation.
2.1 | RWI Training Day - July - focusing on reading section of lesson | ST | 2024-07-22 | 2024-07-22 | 500 | MC |  |  | Governors
2.1 | Monitor staff modelling of fluency | ST | 2024-09-23 | 2024-10-18 | HLTA cover £102 | MC |  | 95% of staff modelling fluency effectively | Governors
2.1 | Coaching/support for identfied staff | ST | Jan/Feb 2025 | Jan/Feb 2025 | 0 | MC |  |  | Governors
2.1 | Further monitoring | ST | Mar/Apr | Mar/Apr | HLTA cover £102 | MC |  | 100% of staff modelling fluency effectively | Governors
2.2 For staff to consistently use strategies introduced by reader leader in RWI/reading lessons
2.2 | Fluency training day one - Literacy hub | ST EJ | 2024-09-19 | 2020-09-29 | HLTA cover £205 | MC |  | ST and EJ attended and following this trialled stategies with small groups of children. | Governors
2.2 | Discuss with SLT | ST | 2024-09-24 | 2024-09-24 | 0 | NA |  |  | Governors
2.2 | Staff meeting intro - teachers | ST | 2024-10-10 | 2024-10-10 | 0 | NA |  |  | Governors
2.2 | KS1 teachers to trial use of echo reading | KS1 teachers | 2024-10-01 | 2024-12-01 | 0 | MC |  |  | Governors
2.2 | Fluency training day two - Literacy hub | ST EJ | 2024-11-04 | 2024-11-04 | HLTA cover £205 | NA |  |  | Governors
2.2 | Relook/speak with Kally about how fluency taught in RWI (RWI dev day) | ST DN | 2024-11-01 | 2024-11-01 | £1500 per year | MC |  | See report from RWI consultant | Governors
2.2 | Staff meeting - session two | ST | 2024-12-12 | 2024-12-12 | 0 | MC |  |  | Governors
2.2 | TA meeting | ST | 2025-01-01 | 2025-01-01 | 0 | MC |  |  | Governors
2.2 | Revise the texts used on the reading spine and update as required | ST AT DN | 2025-01-01 | 2025-02-01 | 0 | MC |  | See reading spine | Governors
2.2 | Develop fluency structure | ST EJ | 2024-12-01 | 2024-12-01 | 0 | MC |  | New timetables implemented | Governors
2.2 | Share fluency structure with all staff - monitor delivery and offer coaching/support | ST | 2025-01-01 | 2025-04-01 | 0 | MC |  | ST dropped into a number of sessions and provided on the spot coaching as needed | Governors
2.2 | Reading leader to gather feedback from staff on the structure of fluency. | ST | 2025-02-01 | 2025-02-01 | 0 | MC |  | Discussed in staff meeting. Postive feedback | Governors
2.3 Assessment processes meet the needs of our pupils and interventions are in place for children not on track in reading.
2.3 | Half-termly RWI assessments | ST MC DN | Half-termly |  | 0 | ST MC |  |  | Governors
2.3 | Implement RWI and reading fluency interventions for identified pupils. | ST MC DN | Half-termly |  | 0 | ST MC |  |  | Governors
2.3 | Analyse progress of children with interventions | ST MC | 2024-10-01 | 2024-10-01 | 0 | ST MC |  | Progress Y1 - 65% inc EHCP 77% ex EHCP Y2 - 66% inc EHCP 69% exc EHCP Y2 Fluency - 86% | Governors
2.3 | SLT to read Strong foundations in the first years of school. | SLT | 2024-11-01 | 2024-11-01 | 0 | ST MC |  |  | Governors
2.3 | Introduce York Assessment for fluency/comp | ST EJ | 2025-01-01 | 2025-01-01 |  | ST MC |  | Introduced for selected children as needed | Governors
2.3 | Analyse end of term data. | ST MC | 2024-12-01 | 2025-01-01 | 0 | ST MC |  | See below | Governors
2.3 | Phonic Screening | KS1 teachers | Feb-25 |  | 0 | ST MC |  | Baseline Y1 39% Feb Y2 72% | Governors
2.3 | Analyse progress of children with interventions | ST MC | 2025-02-01 | 2025-02-01 | 0 | ST MC |  | Progress FS2 - 53% Y1 - 71% inc EHCP 79% ex EHCP Y2 - 72% inc EHCP 73% exc EHCP Y2 Fluency - 95% | Governors
2.3 | Phonic screening | KS1 teachers | June-25 | June-25 | 0 | ST MC |  | Y1 69% Y2 84% | Governors
2.4 70-80% of pupils achieve age related expectations in reading (on track in RWI, Y1 phonics)
2.4 | Baseline reading data | MC | Sep-24 |  | 0 | ST |  | 34% FS2 Autumn 1 57% Y1 53% Y2 Reading | Governors
2.4 | Making it Real CPD - early language development | BT | 2024-09-18 | 2024-09-25 | HLTA cover £205 | NA |  | BT attended training | Governors
2.4 | Making it Real team to engage with parents at Nursery stay and play | BT | 2024-10-08 | 2024-10-11 | 0 | MC |  | Suceesful event with 3/3 families signing up for project. | Governors
2.4 | Make it Real practioners to carry out direct work with identified families. | BT |  |  | 0 | MC |  | Successful engagement with 2 out of 3 families. | Governors
2.4 | BT to engage with Make it Real network meetings | BT | Termly |  | 0 | MC |  | BT has reguarly attended Make it Real meetings. As a result BT has planned a number of parent events for 2025-26 to promote literacy development in the home. | Governors
2.4 | Reading for pleasure CPD | ST | 2024-10-09 | 2024-10-09 | HLTA cover £205 | MC |  | Day one attended. Decided not to continue as KS2 focussed | Governors
2.4 | Reconsider RWI and KS1 timetable | SLT | 2024-09-25 | 2024-09-26 | 0 | ST MC |  | RWI now 50 mins allowing more time for reading | Governors
2.4 | Reading in the curriculum course - Literacy Hub | AC | 2024-11-21 | 2024-11-21 | 0 | NA |  | Course cancelled | Governors
2.4 | Promote Rainbow Reading challenge - newsletters, social media, open afternoons | Teachers | 2024-09-01 | 2025-07-01 | 0 |  |  | Increased engagement this year but still lots of work to do with some families. 78% of children started the challenge compared to 70% last acadmic year. 48% of children completed the challenge (no data from last year) | Governors
2.4 | Monitor reading data | MC | 2024-10-01 | 2024-10-01 | 0 | ST |  | 35% FS2 58% Y1 55% Y2 | Governors
2.4 | Monitor reading data | MC | 2024-12-01 | 2024-12-01 | 0 | ST |  | 34% FS2 52% Y1 48% Y2 | Governors
2.4 | Monitor reading data | MC | 2025-02-01 | 2025-02-01 | 0 | ST |  | 48% FS2 55% Y1 39% phonics 53% Y2 | Governors
2.4 | Monitor reading data | MC | 2025-04-01 | 2025-04-01 | 0 | ST |  | 46% FS2 (3 children left) 52% Y1 42% phonics 62% Y2 | Governors
2.4 | Monitor reading data | MC | 2025-05-01 | 2025-05-01 | 0 | ST |  | 52% FS2 (3 children left) 52% Y1 77% Y2 | Governors
2.4 | Monitor reading data | MC | 2025-07-01 | 2025-07-01 | 0 | ST |  | 60% FS2 67% non EHCP 54% Y1 60% non EHCP 69% Y1 phonics 62% Y2 Reading 66% non EHCP 84% Y2 phonics RWI 59% of Y1 children working at RWI group blue+ compared to 38% at the end of 2023-24 77% Y2 (RWI) | Governors

## Priority 3
Objective | Action | Lead person | Start date | Finish date | Costs | Monitoring | RAG Rating | Status: Progress and/or Impact | Evaluator
3.1 100% of targets in PLPs are SMART, focus on area of need and have clear entry and exit points
3.1 | Monitoring shows that targets in 80% of PLPs are SMART. SENDCo to support staff where needed. | ES | 2024-10-01 |  | Edukey - £1080 | ES |  | 90% of targets in PLPs are SMART. | Link governor - CM/LM
3.1 | Monitoring shows that targets in 80% of PLPs are SMART. SENDCo to support staff where needed. | ES | 2025-03-01 |  | 0 | ES |  | 95% of targets in PLPs are SMART. | Link governor - CM/LM
3.1 | Monitoring shows that targets in 80% of PLPs are SMART. SENDCo to support staff where needed. | ES | 2025-05-01 |  | 0 | ES |  | 100% of targets in PLPs are SMART. | Link governor - CM/LM
3.2 100% of staff have improved understanding of Intensive interaction, The Curiosity Programme, Attention Autism, Sensory provision. Staff deliver programmes with confidence
3.2 | Intensive interaction CPD with Paul Cook | MC | 2024-09-26 | 2024-09-26 | 100 | ES |  | Monitoring shows that staff are using intesive interaction throughout the school. | Link governor - CM/LM
3.2 | BT attend Curiosity CPD | BT | 2024-09-10 | 2024-09-10 | HLTA cover £205 | ES |  | Attended | Link governor - CM/LM
3.2 | Disseminate Curiosity CPD | BT | 2024-12-05 | 2024-12-05 | 0 | ES |  | Staff meeting Autumn 2 | Link governor - CM/LM
3.2 | Begin to implement Curiosity activities with identied children | Tas | Spring 25 | Summer 25 | 0 | ES |  | Staff now regularly using Curiosity activities with identified EHCP pupils. Some children have progressed to Bucket time.
3.2 | Complete Attention Autism referals | ES/MC | 2024-10-01 | 2024-11-01 | 0 | ES |  | Complete Nov 2024 | Link governor - CM/LM
3.2 | EYFS team to model Attention Autism in FS2 | LC | 2024-11-01 | 2024-11-01 | 0 | ES |  | Modelled by Abby Germaney (EYFS team) | Link governor - CM/LM
3,2 | FS2 staff to model Attention Autism to N and Y1 staff | LC | 2024-11-01 | 2024-11-01 | 0 | ES |  | Some staff yet to observe sessions. Update Feb - all relevant staff now observed sessions | Link governor - CM/LM
3.2 | Begin to implement Attention Autism in N-Y1 | TAs | Spring 25 | Spring 25 | 0 | ES |  | Screening forms completed and sessions implemented with identifed children. | Link governor - CM/LM
3.2 | Continue to implement Attention Autism | TAs | Summer 25 | Summer 25 | 0 | ES |  | Sessions have continued with some children have developed to next stage of progreamme | Link governor - CM/LM
3.2 | BUSS (Building Underdevloped Sensory Systems) CPD | ES DN BT MC LC ZD AM | 2025-03-01 | 2025-06-03 | HLTA cover £205 per day | ES |  | All identified staff attended
3.2 | Complete BUSS screening with pupils ideintied by BT and ES. | ES BT | 2025-06-03 | 2025-06-03 | 0 | ES |  | Screening forms complete and children chosen for LEAPLETS sessions. Permission agreed with parents. LEAPLETS sessions to start Autumn 2025.
3.3 100% of children with SEND achieve the best possible outcomes
3.3 | SENDCo complete all Y2 special annual reviews | ES | 2024-09-01 | 2024-10-01 | 0 | MC |  | All complete by October half-term | Link governor - CM/LM
3.3 | SEND progress meeitngs | ES Teachers | 2024-10-01 | 2024-10-01 | 0 | ES |  | See meeting notes | Link governor - CM/LM
3.3 | EYIF applications | ES BT | 2024-10-01 | 2024-10-01 | HLTA cover £205 per day | ES |  | Submitted with funding secured | Link governor - CM/LM
3.3 | SEND Learning walk | ES | 2025-12-01 | 2025-12-01 | 0 | MC |  | See feedback sheet | Link governor - CM/LM
3.3 | EYIF applications | ES BT | 2025-03-01 | 2025-03-01 | HLTA cover £205 per day | ES |  | Submitted with funding secured | Link governor - CM/LM
3.3 | SEND progress meeitngs | ES Teachers | 2024-10-01 | 2024-10-01 | 0 | ES |  | See meeting notes | Link governor - CM/LM
3.3 | Analyse progress of SEND pupils | ES | 2025-04-01 | 2025-04-01 | 0 | ES |  | See SEND data reports with priorities for Summer term. Data is lower in some classes. We believe this is due to inappropriate EHCP targets for some pupils. To be addressed through annual/emergency annual reviews. | Link governor - CM/LM
3.3 | EYIF applications | ES BT | 2025-06-01 | 2025-06-01 | 0 | ES |  | Submitted with funding secured | Link governor - CM/LM
3.3 | Delivering Better Value SEND review | MC | 2025-05-01 | 2025-05-01 | 0 | MC |  | Feedback was overwhelmingly positive and SEND audit score improved from 64% in Nov 2023 to 91% in June 2025. See final report for more detailed feedback. | Link governor - CM/LM
3.3 | SEND progress meeitngs | ES Teachers | 2024-10-01 | 2024-10-01 | 0 | ES |  | See meeting notes | Link governor - CM/LM
3.3 | Analyse progress of SEND pupils | ES | 01/07/2025 | 01/07/2025 | 0 | MC |  | Overall progress has improved as follows (0 is expected progress)- Communication & Interaction Feb -0.8 July +0.008 Cognition & Learning Feb -0.46 July -0.075 Sensory & Physical Feb -0.73 July +0.10 Social, Emotional, Mental Health Feb -0.98 July +0.10 See full progress report for detailed information about progress | Link governor - CM/LM