## School development plan
Queen Mary Infant and Nursery School Priorities |  | SEF Reference | Development plan 25-26 - priorities and milestones (see priority tabs for detailed actions) | [8 empty] | Notes: This document shows the 3-4 priorities for the current academic year. It is populated with some examples. The priorities are listed and then the intended outcomes (objectives) are set out - this is the ciritcal part of development planning. Be very clear what your outcome will be - be precise. After setting out your objectives for the END OF THE YEAR you can then work out the trajectory of how you will achieve that - this is shown through the milestones which will be achieved. These can then be BRAG rated to show governors how work is progressing. In this document add colours using the fill tool (Home tab) The detailed actions sit behind this summary plan and for each priority the actions will be listed on a new tab - see example on priority 1 tab and shorter example on priority 2 tab. Use the + button to add new tabs. | Evaluation code
|  |  | Objectives What will end points look like? | Milestones | [9 empty] | off track - unlikely to be completed
|  |  |  | Autumn 1 | Autumn 2 | Spring 1 | Spring 2 | Summer 1 | Summer 2 | Impact Commentary | Next Steps |  |  | in danger of going off track
1 | Improve literacy outcomes across the school so that they are in line with/closer to national standards |  | 1.1 Embed strategies to support pupils fluency in their reading to improve outcomes so they are in line with/closer to national standards. | Following on from school improvement visit (July 2025), SLT to further monitor echo reading to - review the point at which it is introduced. - refine the approach so that it can be consistently delivered - establish staff/colour groups which may need extra support (baseline percentage to be added after monitoring). Baseline (end of Autumn 1) 76% of pupils have started reading rainbow 39% progressing through rainbow reading challenge (read more than 15 times). | Staff understand and apply refinements to echo reading approach. Monitoring shows that 80% of staff are able to effectively and consistently support pupils to read fluently through echo reading sessions. Parents/carers develop their understanding of the school's approach to reading fluency. | 100% of staff identifed as needing support receive coaching from reader leader. % of pupils progressing through reading rainbow challenge increases through targeted interventions and reading club. | 90% of staff are able to effectively and consistently support pupils to read fluently through echo reading sessions. Outcomes in reading are closer to targets/ national standards. % of pupils progressing through reading rainbow increases through targeted interventions and reading club. | 100% of staff identifed as needing further support receive coaching from reader leader. Nursery phonics coaching delivered by EYFS lead after observations. Improved delivery from all staff. Nursery pupils added to the portal so 'Reader Leader' could monitor progess the same as whole school. | 100% of staff are able to effectively and consistently support pupils to read fluently through echo reading sessions. 90% in Summer monitoring Outcomes in reading are in line with/closer to national standards. 75% of pupils complete reading rainbow challenge (compared to 48% last year) 42% completed challenge. FS2 - 37% Y1 - 67% Y2- 22% | End of year data shows Year 1 phonics has increased from 69% in 2024-25 to 73% in 2025-26.This increases to 81% when removing disapplied children. Year 2 has increased from 84% in 24-25 to 87% 2025-26 when removing disapplied pupils it is 89% 56% of Y1 pupils were on track in reading at the end of 24-25, 66% of the same group of pupils were on track at the end of 25-26. 32% achieved GDS In 2025 59% of pupils reached blue+) 2026 – 69% reached blue plus, 76% when pre-verbal pupils are removed from data | Further monitor echo reading. Look at those teaching groups who are key for echo reading and provide more support to those new the blue grey etc. |  |  | on track
|  |  | 1.2 Improve outcomes in writing across the school so they are in line with/closer to national standards. | SLT and writing lead understand the key points of DFE Wriiting Framework and Strong Foundations. Through monitoring, the new writing lead begins to understand the current writing curriculum and provision within school. Through visits to local scools, the writing lead and KS1 lead further develop their understanding of Talk for Writing. Y1 teachers consistently deliver build/hold a sentence sessions for identified children. Y2 teachers develop their understanding of build/hold a sentence. | Through CPD - the writing lead further develops her understanding of DFE Writing Framework and Strong Foundations. She begins to understand how to develop a writing curriculum which is reflective of these documents. Through use of DFE Writing Framework audit tool, the new writing lead further develops her understanding of the current writing curriculum/provision within school and identfies strengths and areas for development. | Teachers develop their understanding of the DFE Wriiting Framework and Strong Foundations. Through use of DFE Writing Framework audit tool, the new writing lead further develops her understanding of the current writing curriculum/provision within school and identfies strengths and areas for development. A consistent, school-wide approach to handwriting that follows a clearly sequenced progression and supports the gradual acquisition of skills is in place. Monitoring shows that 80% of teachers are able to meet expections of the Writing Framework in handwriting lessons. | 100% of staff identifed as needing support with teaching of handwriting instruction receive coaching from writing lead. | Through use of DFE Writing Framework audit tool, the new writing lead develops her understanding of the leadership of writing and writing in Reception and identifies strengths and areas for development. | Further monitoring of provision for pupils identifed as needing SEN support shows that appropriate strategies and approaches are in place in 80-90% of classes. Further monitoring not completed due to Annual Review load - 10 full weeks of SENDCo time tak | SIP report July 2026 'Leaders have focused on consistency in handwriting. Writing models by teachers, were consistent around the school today. There was evidence in books of letter formation being addressed.' 'Talk for writing has a positive impact on the language pupils use in their writing.' 'Talk for writing has a positive impact on the language pupils use in their writing. Baseline assessments are useful in capturing entry points to show how pupils are progressing.' 'Scaffolds for writing have been carefully thought through e.g. Using lines to indicate the number of words in a sentence, using talk-tins to help pupils hold their ideas and then using widgets to support.' All year groups have seen an increase in writing data since 2025 | Literacy leader to access further training to support her in reviewing the curriculum and develop her leadership skills Liaise with William Barcroft to understand the progression of spelling and the scheme which is used there. Approach the English hub for support to either plan a spelling programme or access an appropriate scheme for infants if William Barcroft don’t share their scheme. Refine milestones in writing to set out expectations on a ½ termly basis.
2 | Further develop inclusive practice and ensure reasonable adjustments are in place to overcome the barriers that pupils face |  | 2.1 To further develop pupils emotional literacy so they are more able to manage their feelings effectively. | Staff understand the benefits of social and emotional learning. They begin to introduce TGMC (The Good Morning Club) resources to pupils so they are better able to understand the following feelings and know strategies to help them manage these feelings - Happy, sad and angry. Leaders establish and understand a baseline of behavioural incidents using data from Autumn 1. | Pupils are better able to understand the following feelings and know strategies to help them manage these feelings - Calm, tired and proud Monitoring shows that staff are beginning to use TGMC resources in class. | Data monitoring shows that behavioural incidents are reducing over time. Monitoring of behaviour data shows that there has not been a clear reduction in incidents - see HT report Spring 2026 There has been a reduction in behaviour incidents for specific pupils - case studies to be put together. | Monitoring shows that TGMC resources are becoming embedded. | Behaviour presentation | Data monitoring shows that behavioural incidents have reduced over time. | Behaviour Incidents 2025-26 | Overall behaviour incidents have decreased. It is noted near Christmas incidents increase due to excitement and off timetabke more. There is also a riseIn the Summer term due which is again due to transition and off timetable . As SLT we are going to put strategies in place to help minmise this such as spreading out certain events like QMA Fest and Sports day.
W:\SLT FILE\GOVERNORS\Headteacher reports\HT Report Spring 2026.pdf
|  |  | 2.2 To further develop physical and sensory provision to ensure pupils receive effective support and specialist guidance when required. | 95% staff attend 'Let's Go Potty' training. 75% of BUSS sessions are attended by identified families. 80% attendance | 75% of BUSS sessions are attended by identified families. Impact review shows that identified pupils have improved sensori-motor skills. 80% attendance Impact report shows all pupils involved have made good progress. | Monitoring shows that 80% staff are implementing 'Let's Go Potty' effectively and identified pupils are making progress with toilet training. There has been a reduction in the percentage of pupils in nappies - see report. | 100% of staff identifed as needing further support implementing Let's Go Potty receive coaching from SENDCO. - discussion with staff, parents and monitoring shows staff are committed and keep conversation going Leaders and teachers identify further pupils in FS2 who would benefit from BUSS - done | Monitoring shows that 90-100% staff are implementing 'Let's Go Potty' effectively.- discussion shows progress with toileting for those in nappies e.g. sitting on toilet etc. 75% of second group of BUSS sessions are attended by identified families. Impact review shows that identified pupils have improved sensori-motor skills. - 86% attendance at halfway point | Monitoring shows that identified pupils are continuing to make progress with toilet training. - discussion Data shows progress - see below 75% of second group of BUSS sessions are attended by identified families - final total is 74.3%. (persistent absence participants affected this greatly)
|  |  |  | % in nappies Nursery 18/52 34.6% FS2 16/80 20% Year 1 6/65 9.23% Year 2 2/72 2.78% | Data Report BUSS group intervention.odt | % in nappies Nursery 1/55 27.27% FS2 11/80 13.75% Year 1 6/65 9.23% Year 2 1/72 1.39% |  |  | % in nappies Nursery 12/75 16% FS2 11/78 14% Year 1 6/6 9.7% Year 2 1/62 1.6%
|  |  | 2.3 Leaders and staff have a secure understanding of the needs of disadvantaged pupils, those with SEND, those who are known (or previously known) to children’s social care, and those who may face other barriers to their learning and/or well-being. Appropriate strategies and approaches are in place to overcome barriers and are understood and implemented by staff. | Using Insight, teachers develop a good understanding of the range of barriers all vulnerabilities in their class. Monitoring of provision for pupils identifed as needing SEN support shows that appropriate strategies and approaches are in place in 80% of classes. 71% (5/7) of classes |  | 100% of teachers are provided with guidance and support around adaptive teaching so that all teachers ensure vulnerable pupils get the best support first. - SEND reviews show discussions held to give guidance and support to individual staff directly regarding each child with SEND in class including EHCP. All raised issues followed up by SENDCo and staff. |  | Assessment processes effectively track small steps of progress for pupils with SEND. - SEND review meetings held - discussion & support given to all teachers. Small Steps documents not yet implemented for K school support - consider PIVATS for next year. Monitoring of provision for children with EHCPs shows that appropriate strategies and approaches are in place to overcome barriers and are understood and implemented by staff. - Monitoring showed range of strategies in place. Any issues were followed up by teachers, support staff and SENDCo following monitoring and regular SEND reviews. | Further monitoring of provision for pupils identifed as needing SEN support shows that appropriate strategies and approaches are in place in 80-90% of classes. Further monitoring not completed due to Annual Review load - 10 full weeks of SENDCo time taken up by these alone aside from EHCaR, EYIF, SALT, SEND review etc. |  | Small Steps documents not yet implemented for K school support - consider PIVATS for next year. Consider workload of SENDCo and ways to monitor SEND provision.
3 | Ensure the EYFS curriculum is expertly designed and sets out, for each area of learning, the knowledge and skills that children need to secure in preparation for later learning. |  | 3.1 Through involvement in the Jigsaw Math Trial -Improve the quality of early mathematics teaching in Reception -Improve pupil outcomes and children's early mathematical understanding. -Build solid foundations in maths for young children (four- to five-year-olds). -Enhance practitioners' subject knowledge and confidence in teaching early years mathematics. |  | 100% of FS2 teachers, FS2 class TAs and Maths lead further develop their subject knowledge through attendance at first CPD session - Developing Early Number Sense. | 100% of FS2 teachers, FS2 class TAs and Maths lead further develop their subject knowledge through attendance at second CPD session - Creating a Mathematical Classroom. 100% of involved staff carry out gap task. | 100% of FS2 teachers and Maths lead further develop their subject knowledge through attendance at third CPD session - Exploring Pattern, Shape and Spatial Reasoning. | 100% of FS2/KS1 teachers and Maths lead further develop their subject knowledge through attendance at fourth CPD session - Mathematical Talk and Questioning | 100% of FS2/KS1 teachers and Maths lead further develop their subject knowledge through attendance at final CPD session _ Reasoning and Problem Solving. Outcomes in maths are in line with/closer to national standards | Outcomes in EYFS Maths are higher than last academic year and show good progress from baseline Number 2024 data - 55% 2025 Baseline 46% Summer 2026 62% Nat 79% Numerical Patterns 2024 data - 59% Baseline 42% Summer 2026 67% Nat 79%
|  |  | 3.2 Staff interactions with children are highly effective in improving children's communication and language and vocbulary. This is the case aross all areas of learning , especially for disadvantaged children and those with SEND. |  | Through CPD, EYFS lead further develops her knowledge and understadning of interactions. Using Communication Trust tool, EYFS lead to monitor quality of interactions across EYFS to establish baseline. | 100% EYFS staff to attend in house CPD in relation to interactions. Further monitoring shows that the quality of interactions is improving and the Communication Trust audit score increases. EYFS lead uses audit tool to identify strengths and areas for development. SIP report Jan 2026 shows that quality of interaations have improved. | Further CPD, support, modelling and/or coaching is provided to address areas for development and improve practice of identifed staff. Shared feedback with and monitored. |  | Monitoring shows that the quality of interactions further improves and the Communication Trust audit score continues to increase. EYFS lead uses audit tool to identify strengths andany further areas for development.
|  |  | 3.3 Ensure ambitious milestones for continuous provison are effectively planned to support children's progression through the EYFS. | HT and SIP (school improvement partner) monitor continuous provision across EYFS to establish strength and areas for development. See SIP report Autumn 2025 | EYFS lead, Nursery lead and HT begin to develop milestones documents which for continuous provision. Seek feedback from EYFS staff and further refine documents. | Further develop milestones documents with support of school improvement advisior. EYFS staff begin to implement milestones documents. See Jan SIP report for details of milestones documents. | Monitoring shows that staff are becoming more confident in implementing milestones for continuous provision. | Staff feedback informs further refinements to milestones document. | Monitoring shows that Summer term milestones for continuous provision are being implemented across EYFS. Staff feedback informs further refinements to milestones document for 2026-27. |  | Vocabulary to be added to milstones documents for 26/27 Create Miletsones documents for reading, writing and Maths
|  |  |  | W:\SLT FILE\SLT FILES\MC\School Improvement\2025-26\SIP Visit 17.9.25.pdf |  | W:\SLT FILE\SLT FILES\MC\School Improvement\2025-26\SIP visit 22.1.26.pdf |  | \\qma-dc\Wpdata\SLT FILE\MONITORING\2025-26\SEND\Summer Term monitoring 2026

## Priority 1
Objective | Action | Lead person | Start date | Finish date | Costs | RAG Rating | Monitoring | Status: Progress and/or Impact | Evaluator | Notes: Exemplar of the detailed/ operational actions to support a priority example taken from the previous tab (1.1) This was sorted by date after writing actions. Explore using the sort function to see how actions can be prioritised by date, person or RAG rating. EXCEL TIPS To extend box for RAG rating click on last colored cell, drag bottome left corner down the cells as far as is needed. To create a new page - copy layout onto a new tab. Then to add sort/ filter fuction highlight the column you wish to sort - Right click and choose sort or filter.
1.1 | Further CPD for all staff in relation to echo reading. Share feedback from JR report Summer 25 | MC ST | Sep 2025 | Sep 2025 | £0
1.1 | Adjust RWI/echo reading timetable for red-orange groups | ST | Sep 2025 | Sep 2025 | £0
1.1 | Monitoring of echo reading | ST | Sep 2025 | Sep 2025 | £0
1.1 | Analyse 2024-25 data in relation to attendance and reading at home. Identify which children need extra reading practice. | MC ST | Oct 2025 | Oct 2025 | £0
1.1 | Monitor RWI data | MC ST DN | Oct 2025 | Oct 2025 | 0
1.1 | Further monitoring of echo reading | ST | Oct 2025 | Jan 2026 | 0
1.1 | Two development days with Kally | ST MC | Nov 2025 | April 2026
1.1 | Monitoring of Talk through Stories. | ST | Nov-Dec 2025 | Dec 2025 | £0
1.1 | Reader leader to provide coaching as required | ST | Dec 2025 | Feb 2026
1.1 | Monitor RWI and reading data | MC ST DN | Dec 2025 | Dec 2025
1.1 | Monitor RWI data | MC ST DN | Feb 2026 | Feb 2026
1.1 | Monitor RWI and reading data | MC ST DN | April 2026 | April 2026
1.1 | Monitor RWI data | MC ST DN | May 2026 | May 2026
1.1 | Monitor RWI and reading data | MC ST DN | July 2026 | July 2026
1.1 | Developing a progressive reading curriculum course | ST | Jan 2026 | June 2026
1.1 | Unlocking every reader course | ST | Jan 2026 | March 2026
1.2 | Provide time for writing lead to read The Writing Framework and Strong Foundations | AT | Sep 2025 | Sep 2025 | HLTA cover
1.2 | Wrtiing lead to monitor current writing provision | AT | Sep 2025 | Sep 2025 | HLTA cover
1.2 | SLT and writing lead to watch DFE webinar in relation to The Writing Framework | AT SLT | 30/09/2025 | 30/09/2025 | £0
1.2 | SLT and writing lead to watch LEAD webinar in relation to The Writing Framework | AT SLT | 30/10/2025 | 30/10/2025 | £0
1.2 | Writing lead to audit handwrting using DFE audit tool | AT | Oct 2025 | Nov 2025 | HLTA cover
1.2 | Update handwriting policy and share with staff | AT | Oct 2025 | Nov 2025 | HLTA cover
1.2 | CPD for teaching staff in relation to The Writing Framework and Strong Foundations | AT MC | Nov 2025 | Nov 2025 | £0
1.2 | Writing lead to attend LEAD training - Developing your School's Transcription Curriculum | AT | 21/10/2025 | 21/10/2025 | HLTA cover
1.2 | Writing lead to attend LEAD training- Developing a Progressive Writing Curriculum | AT | 2025-12-02 | 2025-02-02 | HLTA cover
1.2 | Writing lead to audit using DFE audit tool | AT | Oct 2025 | Nov 2025 | HLTA cover
1.1
1.1
1.1
1.1
1.1
1.1
1.1
1.1
1.1
1.1
1.1
1.1
1.1
1.1
1.1
1.1
1.1

## Priority 2
Objective | Action | Lead person | Start date | Finish date | Costs | Monitoring | RAG Rating | Status: Progress and/or Impact | Evaluator
2.1 | Staff CPD - ST to introduce TGMC resources to teachers | ST | Sep 2025 | Sep 2025
2.1 | Staff begin to introduce TGMC (The Good Morning Club) resources for happy, sad and angry. | Teachers | Sep 2025 | Oct 2025
2.1 | Leaders establish and understand a baseline of behavioural incidents using data from Autumn 1. | ST MC | Oct half-term | Oct half-term
2.1 | Introduce TGMC resources for Calm, tired and proud |  | Oct 2025 | Dec 2025
2.1 | Data monitoring shows that behavioural incidents are reducing over time. | ST MC | Feb half-term | Feb half-term
2.1 | Data monitoring shows that behavioural incidents are reducing over time. | ST MC | Jul 2026 | Jul 2026
2.2 | 95% staff attend 'Let's Go Potty' training. | ES | Sep 2025 | Sep 2025 |  | register
2.2 | 75% of BUSS sessions are attended by identified families. 80% attendance | ES | Sep 2025 | Dec 2025 |  | ES and BUSS data
2.2 | Impact review shows that identified pupils have improved sensori-motor skills. | ES BT | Dec 2025 | Dec 2025 |  | ES and BUSS data
2.2 | Leaders and teachers identify further pupils in FS2 who would benefit from BUSS sessions. | ES with EYFS teachers |  |  |  | BT and LC
2.2 | Monitoring shows that 80% staff are implementing 'Let's Go Potty' effectively and identified pupils are making progress with toilet training. | ES | Jan 2026 | Feb 2026
2.2 | 75% of second group of BUSS sessions are attended by identified families. | ES BT | Jan 2026 | April 2026 |  | ES and BUSS data |  | 74.3%
2.2 | 100% of staff identifed as needing further support implementing Let's Go Potty receive coaching from SENDCO. | ES | March 2026 | April 2026 |  | ES
2.2 | Monitoring shows that 90-100% staff are implementing 'Let's Go Potty' effectively | ES | May 2026 | June 2026 |  | ES |  | from Nappy data nd EHCP reviews
2.2 | Monitoring shows that identified pupils are continuing to make progress with toilet training. | ES | June 2026 | July 2026 |  | ES |  | from Nappy data nd EHCP reviews
2.3 | Using Insight, teachers develop a good understanding of the range of barriers all vulnerabilities in their class. | MC | Sep 2025 | Sep 2025
2.3 | Leaders have a good understanding of barriers across the school. | MC | Sep 2025 | Sep 2025
2.3 | Monitoring of provision for pupils identifed as needing SEN support shows that appropriate strategies and approaches are in place in 80% of classes. 71% (5/7) of classes | ES | Sep 2025 | Oct 2025 |  | ES monitoring Autumn Term 2025 |  | 5/7 classes Feedback given SEND review meetings for guidance to all teachers with goals
2.3 | Assessment processes effectively track small steps of progress for pupils with SEND. | ES |  |  |  | ES |  | Awaiting decision on format e.g. PIVATS, Developmental etc.
2.3 | Monitoring of provision for children with EHCPs shows that appropriate strategies and approaches are in place to overcome barriers and are understood and implemented by staff. | ES |  |  |  | ES |  | Monitoring in Spring Term
2.3 | 100% of teachers are provided with guidance and support around adaptive teaching so that all teachers ensure vulnerable pupils get the best support first. | ES |  |  |  | ES |  | SEND review meetings all actions reviewed and followed up

## Priority 3
Objective | Action | Lead person | Start date | Finish date | Costs | Monitoring | RAG Rating | Status: Progress and/or Impact | Evaluator
3.1 | 100% of FS2 teachers, FS2 class TAs and Maths lead further develop their subject knowledge through attendance at first CPD session - Developing Early Number Sense. | DN EJ | 2025-09-01 | 2026-06-01 |  | All teachers FS2 Tas
3.1 | 100% of involved staff carry out gap task. | DN SS AT | 2025-09-01 | 2026-06-01 |  | SS maternity ED continued
3.1 | 100% of FS2 teachers, FS2 class TAs and Maths lead further develop their subject knowledge through attendance at second CPD session - Creating a Mathematical Classroom. | DN EJ | 2025-09-01 | 2026-06-01
3.1 | 100% of involved staff carry out gap task. | DN SS AT | 2025-09-01 | 2026-06-01
3.1 | 100% of FS2 teachers, FS2 class TAs and Maths lead further develop their subject knowledge through attendance at third CPD session - Exploring Pattern, Shape and Spatial Reasoning. | DN EJ | 2025-09-01 | 2026-06-01 |  | FS2 teachers |  | Numerical pattern has improved more so than number. Summer data 67%
3.1 | 100% of FS2 teachers, FS2 class TAs and Maths lead further develop their subject knowledge through attendance at fourth CPD session - Mathematical Talk and Questioning | DN EJ | 2025-09-01 | 2026-06-01 |  | All QMA teachers |  | All staff to develop number talk into their everyday practise. FS2 enhanced snack time for 2027
3.1 | 100% of FS2 teachers, FS2 class TAs and Maths lead further develop their subject knowledge through attendance at final CPD session - Reasoning and Problem Solving. | DN EJ | 2025-09-01 | 2026-06-01 |  | All QMA teachers
3.1 | Outcomes in maths are in line with/closer to national standards | DN EJ |  | 2026-07-01 |  | % needs |  | Spring 50% on track - Summer 62% on track
3.2 | Through CPD, EYFS lead further develops her knowledge and understadning of interactions. | DN EJ | 2025-09-01 | 2026-06-01
3.2 | Using Communication Trust tool, EYFS lead to monitor quality of interactions across EYFS to establish baseline. | DN | 2025-09-01 | 2026-06-01
3.2 | 100% EYFS staff to attend in house CPD in relation to interactions. | EYFS staff |  |  |  | Nicole to do |  | DN delivered to all staff in FS2 and nursery.
3.2 | Further monitoring shows that the quality of interactions is improving and the Communication Trust audit score increases. | DN |  | 2026-01-01 |  | See SIP report
3.2 | EYFS lead uses audit tool to identify strengths and areas for development. | DN |  | 2026-06-01 |  |  |  | DN monitored in Spring and Summer using audit tool. SIP showed improvements.
3.2 | Further CPD, support, modelling and/or coaching is provided to address areas for development and improve practice of identifed staff. | DN | [5 empty] | DN provided coaching for the delivery of RWI in Spring 2 to enhance delivery. ST and DN monitored this the following week. Baseline for RWI for nursery has improved. Summer 25 5+ sounds = 25 Summer 26 5+ sounds = 26
3.2 | Monitoring shows that the quality of interactions further improves and the Communication Trust audit score continues to increase. | DN | 2025-09-01 | 2026-06-01 |  | to do |  | Data collated 26-27 on sheet devised by DN to improve this further.
3.2 | EYFS lead uses audit tool to identify strengths and any further areas for development. | DN | 2025-09-01 | 2026-06-01
3.3 | HT and SIP (school improvement partner) monitor continuous provision across EYFS to establish strength and areas for development. | MC JR |  | 2026-01-01 |  | SIP report showed improvements
3.3 | EYFS lead, Nursery lead and HT begin to develop milestones documents which for continuous provision. | MC DN BT | 2025-09-01 | 2026-07-01 |  |  |  | Completed it - vocabulary to be added 26-27 to further improve.
3.3 | Seek feedback from EYFS staff and further refine documents. | EYFS staff | 2025-09-01 | 2026-07-01
3.3 | Further develop milestones documents with support of school improvement advisior. | MC DN JR |  | 2026-01-01 |  | vocabulary added
3.3 | EYFS staff begin to implement milestones documents. | EYFS staff |  |  |  | Buddy up day
3.3 | Monitoring shows that staff are becoming more confident in implementing milestones for continuous provision. | DN |  |  |  | feedback needed
3.3 | Staff feedback informs further refinements to milestones document. | EYFS staff
3.3 | Monitoring shows that Summer term milestones for continuous provision are being implemented across EYFS. | DN |  | 2026-06-01
3.3 | Staff feedback informs further refinements to milestones document for 2026-27. | EYFS staff |  |  |  | to do

## Priority 4
Objective | Action | Lead person | Start date | Finish date | Costs | Monitoring | RAG Rating | Status: Progress and/or Impact | Evaluator
3.1